LONGEVITY COACH

Vietnam Sprint Deliverables Spec

Prepared for: James + Edge8 / Dave Hajdu

Sprint Window: Late April 2026 (5 working days)

Document Version: 1.0 | April 15, 2026

CONFIDENTIAL

# 1. Strategic Context

This document is the single source of truth for the Longevity Coach Vietnam sprint with Edge8. It defines what ships during the sprint (Tier 1), what ships in the 4 weeks after (Tier 2), and what goes on the product roadmap (Tier 3).

Objective: Exit the sprint with a launchable B2C longevity platform that can accept paying subscribers on Day 1 post-sprint.

Constraint: 5 working days with Edge8 engineering team + Claude Code. Every hour counts. Scope discipline is non-negotiable.

Principle: Ship Tier 1 at 100% before touching Tier 2. A half-built B2B portal is worth zero; a fully functional B2C app generates revenue.

# 2. Tier Definitions

TIER 1 — MUST SHIP IN VIETNAM: Launch-blocking. Without these, there is no product. 9 deliverables.

TIER 2 — POST-SPRINT (Weeks 2–4): High value but not launch-blocking. Build remotely with Edge8 after sprint. 7 deliverables.

TIER 3 — ROADMAP (Month 2+): Important for scale but not for launch. 6 deliverables.

# 3. Full Deliverables Matrix

| Tier | ID | Deliverable | Description | Owner | Target | Depends On |
| --- | --- | --- | --- | --- | --- | --- |
| TIER 1 — MUST SHIP | 1.1 | Public Landing Page + Pricing | Hero section, value prop, pricing tiers (B2C + B2B), email capture, SEO-ready. Replaces Base44 placeholder. | Edge8 Frontend | Day 1-2 | Copy from James (pre-sprint) |
| TIER 1 — MUST SHIP | 1.2 | Stripe Subscription Billing | B2C monthly/annual plans, free trial logic, webhook handling, customer portal. Migrate from Base44 Stripe stub. | Edge8 Backend | Day 1-2 | Pricing tiers finalised |
| TIER 1 — MUST SHIP | 1.3 | User Onboarding Flow | Sign-up, health intake questionnaire, initial risk assessment, biological age result. First 5-minute user experience. | Edge8 Full-stack | Day 2-3 | Risk engine (1.4) |
| TIER 1 — MUST SHIP | 1.4 | Core Risk Engine + Bio-Age | Multi-domain risk scoring (CV, metabolic, neuro, onco, MSK) + biological age calculation. Port and harden from Base44 MVP. | Edge8 Backend + Claude Code | Day 2-3 | Base44 codebase access |
| TIER 1 — MUST SHIP | 1.5 | Supplement Protocol Generator + PDF | Personalised supplement recommendations with branded PDF export. Port from Base44. | Edge8 Backend | Day 3 | Risk engine (1.4) |
| TIER 1 — MUST SHIP | 1.6 | Dashboard (Consumer) | Post-login home: bio-age, risk scores, supplement plan, next actions, progress tracking. Single-page app feel. | Edge8 Frontend | Day 3-4 | 1.3, 1.4, 1.5 complete |
| TIER 1 — MUST SHIP | 1.7 | Auth + User Management | Email/password + social login, role-based access (consumer, clinician, corp admin), session management. | Edge8 Backend | Day 1 | None |
| TIER 1 — MUST SHIP | 1.8 | Basic CRM / Admin Panel | Internal admin: user list, subscription status, basic analytics, support ticket view. Minimum viable operations tool. | Edge8 Full-stack | Day 4-5 | Auth (1.7) |
| TIER 1 — MUST SHIP | 1.9 | Email Sequences (Onboarding + Nurture) | Welcome series, onboarding drip, trial-to-paid conversion sequence. Integrate SendGrid or Resend. | Edge8 Backend | Day 4-5 | Stripe (1.2) |
| TIER 2 — POST-SPRINT | 2.1 | B2B Corporate Portal | Company registration, QR code staff onboarding, employer-tagged patient records, client dashboard with workforce health metrics. | Edge8 Full-stack | Week 2-3 post-sprint | Auth + CRM (1.7, 1.8) |
| TIER 2 — POST-SPRINT | 2.2 | Clinician Dashboard | Assigned patient list, monthly coaching talking points engine, check-in logging, task assignment per patient. | Edge8 Full-stack | Week 2-3 post-sprint | B2B Portal (2.1) |
| TIER 2 — POST-SPRINT | 2.3 | ROI Calculator (Client-Facing) | Per-employer ROI dashboard: absenteeism reduction, productivity uplift, healthcare cost savings, engagement metrics. | Edge8 Frontend + Data | Week 3-4 post-sprint | B2B Portal (2.1) |
| TIER 2 — POST-SPRINT | 2.4 | WhatsApp Integration (Janet) | Two-way WhatsApp messaging (text + voice), AI-assisted responses, conversation logging, patient-clinician connection. | Edge8 Backend | Week 3-4 post-sprint | Clinician Dashboard (2.2) |
| TIER 2 — POST-SPRINT | 2.5 | AI Recipe Discovery + Meal Planning | Port and enhance from Base44. Personalised meal plans based on risk profile and dietary preferences. | Edge8 Backend + Claude Code | Week 2 post-sprint | Risk engine (1.4) |
| TIER 2 — POST-SPRINT | 2.6 | Sales Funnel Pages | Dedicated landing pages for B2C (longevity seekers) and B2B (corporate wellness), A/B testable, analytics-tagged. | Edge8 Frontend | Week 2 post-sprint | Landing page (1.1) |
| TIER 2 — POST-SPRINT | 2.7 | Social Media Content Templates + Calendar | 30-day content calendar, branded post templates, automated scheduling integration (Buffer/Later). | Claude Code + James | Week 1-2 post-sprint | Brand assets finalised |
| TIER 3 — ROADMAP | 3.1 | Wearable Data Pipeline (Terra + HealthKit) | Full Terra API integration, data normalisation, HealthKit/Google Health Connect sync, real-time dashboard updates. | Edge8 Backend | Month 2-3 | Consumer dashboard (1.6) |
| TIER 3 — ROADMAP | 3.2 | Partner Portal (Coaches, Labs, Imaging) | Multi-role portal: coach dashboard, clinic portal, lab orders, imaging coordination. Ecosystem partnership model. | Edge8 Full-stack | Month 2-3 | B2B Portal (2.1) |
| TIER 3 — ROADMAP | 3.3 | Supplement Affiliate Checkout | White-label supplement purchasing with margin tracking, vendor integration, order management. | Edge8 Full-stack | Month 3 | Supplement engine (1.5) |
| TIER 3 — ROADMAP | 3.4 | Gamification System | Points, streaks, leaderboards, achievement badges. Port from Base44 and enhance. | Edge8 Frontend | Month 3 | Consumer dashboard (1.6) |
| TIER 3 — ROADMAP | 3.5 | Genetic + Microbiome Data Pipelines | Integration with genetic testing providers and microbiome analysis. Advanced personalisation layer. | Edge8 Backend + Data | Month 4+ | Risk engine (1.4) matured |
| TIER 3 — ROADMAP | 3.6 | PEPM Billing (B2B) | Per-employee-per-month billing engine for corporate clients, usage reporting, invoice generation. | Edge8 Backend | Month 3 | B2B Portal (2.1), Stripe (1.2) |

# 4. Day-by-Day Sprint Schedule

This schedule assumes Tier 1 deliverables only. If Tier 1 completes ahead of schedule on Day 5, begin Tier 2 scoping and scaffolding.

| Day | Focus | Deliverables |
| --- | --- | --- |
| Day 0 (Pre-arrival) | Environment Setup | Dev environment, repo structure, CI/CD pipeline, database provisioning, Stripe test mode, domain + SSL |
| Day 1 | Foundation | Auth system (1.7), Stripe billing (1.2), landing page scaffold (1.1), database schema |
| Day 2 | Core Engine | Risk engine port + hardening (1.4), user onboarding flow (1.3), landing page completion (1.1) |
| Day 3 | Feature Build | Supplement generator + PDF (1.5), consumer dashboard scaffolding (1.6), onboarding flow polish |
| Day 4 | Integration + Admin | Dashboard completion (1.6), CRM/admin panel (1.8), email sequences (1.9), end-to-end testing |
| Day 5 | Ship + Buffer | Bug fixes, QA, deployment to production, smoke testing, documentation, Tier 2 scoping for post-sprint |

# 5. Pre-Sprint Checklist (James — Before You Board the Flight)

Every item below must be complete before Day 1 of the sprint. If the engineering team is waiting on you for inputs, you are burning their time and your money.

| Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Finalise pricing tiers (B2C monthly/annual, B2B PEPM rates) | James | April 18 | NOT STARTED |
| Write landing page copy (hero, value prop, testimonials, CTA) | James | April 20 | NOT STARTED |
| Export Base44 codebase + document all API endpoints | James | April 19 | NOT STARTED |
| Prepare brand assets (logo, colour palette, fonts, imagery) | James | April 20 | NOT STARTED |
| Define user onboarding questionnaire (exact questions + scoring) | James | April 21 | NOT STARTED |
| Document risk engine logic (inputs, weights, thresholds per domain) | James | April 21 | NOT STARTED |
| Set up Stripe account + define product/price IDs | James | April 22 | NOT STARTED |
| Confirm hosting/deployment stack with Dave | James + Dave | April 18 | NOT STARTED |
| Share this sprint spec with Edge8 team for review | James | April 17 | NOT STARTED |
| Book daily stand-up slots for sprint week | James + Dave | April 22 | NOT STARTED |

# 6. Technical Decisions Required (Pre-Sprint)

## 6a. Stack Decision

Current MVP is on Base44 (no-code). The sprint needs to determine: are we porting to a production stack (Next.js / React + Node + PostgreSQL), staying on Base44, or using a hybrid approach? This decision changes everything about the week. Recommend: Confirm with Dave by April 18.

## 6b. Hosting + Deployment

Options: Vercel, AWS, Railway, Render. Need CI/CD pipeline from Day 0. Domain: longevity-coach.io (confirm DNS access and SSL certificate).

## 6c. Database

PostgreSQL recommended for relational data (users, subscriptions, risk scores). Consider Supabase for auth + real-time + storage in a single managed service.

## 6d. AI / LLM Integration

Claude Code for sprint velocity. Claude API (Sonnet) for production features: supplement protocol generation, recipe discovery, clinician talking points engine. Define API budget.

## 6e. WhatsApp Provider (Tier 2)

Options: Twilio WhatsApp Business API, 360dialog, MessageBird. Needs business verification (takes 2+ weeks). Start the verification process NOW so it is ready for Tier 2 build.

# 7. Sprint Risks

- Scope creep: James adds features mid-sprint. Mitigation: This document is the contract. No new Tier 1 items after April 20.

- Pre-sprint prep incomplete: Landing page copy, pricing, risk engine logic not documented. Mitigation: Checklist deadlines above. Non-negotiable.

- Base44 migration complexity: Porting logic from no-code platform may be harder than expected. Mitigation: Day 0 environment setup + codebase review.

- Stripe configuration: Payment logic is fiddly. Mitigation: Set up Stripe test mode + product IDs before sprint.

- WhatsApp business verification: Takes 2+ weeks. Mitigation: Start verification immediately; build Tier 2 WhatsApp module after verification completes.

# 8. Sprint Exit Criteria

The sprint is successful if, on the morning after Day 5, the following is true:

- A new user can visit longevity-coach.io, understand the offer, and sign up for a paid subscription.

- After sign-up, the user completes an onboarding health questionnaire and receives their biological age and risk scores.

- The user receives a personalised supplement protocol with a downloadable PDF.

- The user has a dashboard showing their health data, scores, and recommended actions.

- James (as admin) can log in to a CRM and see all users, their subscription status, and basic analytics.

- An automated email welcome sequence fires on sign-up.

- The system is deployed to production with SSL, monitoring, and backup.

If all seven criteria are met, Longevity Coach is launchable. Everything else is optimisation.